## Exceptions
Risk ID | Description | Category | Residual Score | Residual Rating | Exception Type | Severity | Detail | Recommendation
R-006 | Third-party vendor breach exposing customer data | Third-Party Risk | 9 | Medium | Overdue Mitigation | Medium | Risk R-006 mitigation was due 2026-05-31 (30 days ago). Status: Open. | Escalate to risk owner and management. Update mitigation plan with revised due date and justification.
R-004 | Unpatched vulnerabilities in internet-facing systems | Vulnerability Management | 8 | Medium | Overdue Mitigation | Medium | Risk R-004 mitigation was due 2026-06-15 (15 days ago). Status: Open. | Escalate to risk owner and management. Update mitigation plan with revised due date and justification.
R-013 | Physical access to server room by unauthorized personnel | Physical Security | 8 | Medium | No Controls in Place | High | Risk R-013 has no compensating controls. Inherent score: 8. | Design and implement controls. Prioritize based on inherent risk score.
R-013 | Physical access to server room by unauthorized personnel | Physical Security | 8 | Medium | Overdue Mitigation | Medium | Risk R-013 mitigation was due 2026-06-25 (5 days ago). Status: Open. | Escalate to risk owner and management. Update mitigation plan with revised due date and justification.
R-012 | Inadequate segregation of duties in financial approval workflow | ITGC | 6.8 | Medium | No Owner Assigned | High | Risk R-012 has no designated owner. | Assign a risk owner immediately. Risk ownership is required for accountability and tracking.

## Executive Summary
Metric | Value
Report Date | 2026-06-30
Total Risks | 15
Residual Critical (Score 20–25) | 0
Residual High (Score 10–19) | 0
Residual Medium (Score 5–9) | 8
Residual Low (Score 1–4) | 7
Risks with No Controls | 1
Risks with No Owner | 1
Overdue Mitigations | 3
Total Exceptions Flagged | 5
Avg Inherent Score | 11
Avg Residual Score | 5.4
Avg Risk Reduction | 50%
Prepared By | Sandesh Lama Tamang
Reviewed By

## Risk Register
rank | risk_id | risk_description | category | likelihood | likelihood_label | impact | impact_label | inherent_score | inherent_rating | control_description | control_effectiveness | control_factor | risk_reduction_% | residual_score | residual_rating | owner | mitigation_due_date | status
1 | R-006 | Third-party vendor breach exposing customer data | Third-Party Risk | 3 | Possible | 4 | Major | 12 | High | Annual vendor risk assessments | low | 0.25 | 25 | 9 | Medium | Procurement | 2026-05-31 | Open
2 | R-011 | Shadow IT — unauthorized cloud services storing sensitive data | Data Governance | 4 | Likely | 3 | Moderate | 12 | High | CASB solution partially deployed | low | 0.25 | 25 | 9 | Medium | IT Security | 2026-08-29 | In Progress
3 | R-004 | Unpatched vulnerabilities in internet-facing systems | Vulnerability Management | 4 | Likely | 4 | Major | 16 | High | Monthly patching cycle; vulnerability scanning | medium | 0.5 | 50 | 8 | Medium | IT Operations | 2026-06-15 | Open
4 | R-013 | Physical access to server room by unauthorized personnel | Physical Security | 2 | Unlikely | 4 | Major | 8 | Medium |  | none | 0 | 0 | 8 | Medium | Facilities | 2026-06-25 | Open
5 | R-002 | Ransomware attack encrypting critical business data | Cybersecurity | 3 | Possible | 5 | Critical | 15 | High | EDR solution deployed; backups maintained | medium | 0.5 | 50 | 7.5 | Medium | IT Security | 2026-08-29 | In Progress
6 | R-007 | Phishing attacks leading to credential compromise | Cybersecurity | 5 | Almost Certain | 3 | Moderate | 15 | High | Security awareness training; email filtering | medium | 0.5 | 50 | 7.5 | Medium | IT Security | 2026-07-20 | In Progress
7 | R-012 | Inadequate segregation of duties in financial approval workflow | ITGC | 3 | Possible | 3 | Moderate | 9 | Medium | Workflow approval matrix under review | low | 0.25 | 25 | 6.8 | Medium |  | 2026-07-30 | Open
8 | R-001 | Unauthorized access to financial systems via compromised credentials | Access Control | 4 | Likely | 5 | Critical | 20 | Critical | MFA enforced on all financial systems; quarterly access reviews | high | 0.75 | 75 | 5 | Medium | CISO | 2026-07-30 | Open
9 | R-009 | Inadequate backup testing leading to unrecoverable data loss | Business Continuity | 2 | Unlikely | 4 | Major | 8 | Medium | Monthly backup jobs; annual restore test | medium | 0.5 | 50 | 4 | Low | IT Operations | 2026-10-28 | Open
10 | R-010 | Non-compliance with data privacy regulations (GDPR/CCPA) | Compliance | 2 | Unlikely | 4 | Major | 8 | Medium | Privacy policy; DPO appointed | medium | 0.5 | 50 | 4 | Low | Legal | 2026-12-27 | Open
11 | R-008 | Change management failures causing production outages | ITGC | 3 | Possible | 4 | Major | 12 | High | CAB process; change freeze periods | high | 0.75 | 75 | 3 | Low | Change Manager | 2026-09-13 | Open
12 | R-003 | ERP system outage during financial close period | Business Continuity | 2 | Unlikely | 5 | Critical | 10 | High | Disaster recovery plan; redundant systems | high | 0.75 | 75 | 2.5 | Low | IT Operations | 2026-09-28 | Open
13 | R-005 | Insider threat — privileged user misuse of access | Access Control | 2 | Unlikely | 5 | Critical | 10 | High | PAM solution; activity logging | high | 0.75 | 75 | 2.5 | Low | CISO | 2026-08-14 | Open
14 | R-014 | Outdated software documentation increasing onboarding time | Operations | 4 | Likely | 1 | Negligible | 4 | Low | Documentation review scheduled quarterly | medium | 0.5 | 50 | 2 | Low | IT Manager | 2027-01-16 | Open
15 | R-015 | Employee error in manual data entry causing report inaccuracies | Data Integrity | 3 | Possible | 2 | Minor | 6 | Medium | Dual-control review process; automated validation rules | high | 0.75 | 75 | 1.5 | Low | Finance Manager | 2026-11-27 | Closed

## Heat Map
INHERENT IT RISK HEAT MAP — Likelihood × Impact
Likelihood \ Impact | 1-Negligible | 2-Minor | 3-Moderate | 4-Major | 5-Critical
5-Almost Certain | Score: 5 | Score: 10 | Score: 15 R-007 | Score: 20 | Score: 25
4-Likely | Score: 4 R-014 | Score: 8 | Score: 12 R-011 | Score: 16 R-004 | Score: 20 R-001
3-Possible | Score: 3 | Score: 6 R-015 | Score: 9 R-012 | Score: 12 R-006 R-008 | Score: 15 R-002
2-Unlikely | Score: 2 | Score: 4 | Score: 6 | Score: 8 R-013 R-009 R-010 | Score: 10 R-003 R-005
1-Rare | Score: 1 | Score: 2 | Score: 3 | Score: 4 | Score: 5
LEGEND
Low (1–4)
Medium (5–9)
High (10–19)
Critical (20–25)